## Sprint 1 Backlog
PB Name | Description and details | Check Out | Status | Remaining Effort
Player Movement | create a program that can track each of the players consistantly | Myles | Doing | 0
Register Account | Create user registration | Jake | Done | 0
Login/Logout | Create login logout option | Jake | Done | 0
Setup Database | Setup database ready for the site | Jake | Done | 0
Website Design | Design the layout of the site | Will / Jacob | Doing | 0

## Sprint 2 Backlog
PB Name | Description and details | Check Out | Status | Remaining Effort
Heat Map | Display a heat map for each player | Myles | Done | 0
Run external Clips | Implement Tracking script to uploaded videos | Jake | Done | 0
Website Design | Continue refining web design | Will / Jacob | Done | 0
distinct tracking | Refine Tracking | Myles | Done | 0
user friendly interface | Make sure the site is user friendly | Will / Jacob | Done | 0
Upload Clips | option for a user to upload videos | Jake | Done | 0

## Sprint 3 Backlog
PB Name | Description and details | Check Out | Status | Remaining Effort
Competitor Analysis | Track Rallies for each player and display movement trends | Myles | To Do | 20 | Moved to sprint 4
watch clips | allow users to select clips to be analysed | Jake | Done | 0
Distance Travelled | Display movement areas and distance covered by a player | Myles | To Do | 0 | Moved to sprint 4
Player Stats | Allow a user to see player stats | Jake | Doing | 0
search Clips | allow a user to search for certain clips | Jake | Done | 0
Css | make the website look good | Will / Jacob | Done | 0

## Sprint 4 Backlog
PB Name | Description and details | Check Out | Status | Remaining Effort
Account details | allow a user to add more niformation to their account (number, email) | Myles / Jake | To Do | 2
Favourite Clips | Allow users to save their favourite clips | Myles / Jake | To Do | 2
Distance Travelled | Display movement areas and distance covered by a player | Myles | To Do | 10
Competitor Analysis | Track Rallies for each player and display movement trends | Myles | To Do | 15

## Sprint 5 Backlog
PB Name | Description and details | Check Out | Status | Remaining Effort
Polish | Apply the final polish | EveryOne | To Do | 20
Acount Recovery | add account recovery option if you forget password | Jake | To Do | 5
Create Annotations | Allow coaches to create annotations on videos (time Stamps) | Jake | To Do | 2

## Release Burndown Chart
Sprint # | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5
Date | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-08 | 2018-10-15 | 2018-10-22
Day # | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77
Real | 192 | 166 | 155 | 121 | 110 | 90 | 74 | 53 | 42 | 31 | 22
Plan | 192 | 172.8 | 153.6 | 134.4 | 115.2 | 96 | 76.8 | 57.6 | 38.4 | 19.2 | 0
| sprint 1 |  | sprint 2 |  | sprint 3 |  | sprint4 |  | sprint 5
192 | Total Remaining Effort from Product Backlog
5 | Total Number of Sprints - used for ideal plan (red line)
14 | Days in Sprint - used for ideal plan (red line)
2 | Days between daily scrums

## Product Backlog
Name | Description | Priority | Estimated Effort | User Story | Status
Player Movement | Constantly track players movement during a squash game | 1 | 20 | 1 | Done
Competitor Analysis | Track Rallies for each player and display movement trends | 3 | 10 | 2 | To Do | PO = Product Owner
watch clips | allow users to select clips to be analysed | 1 | 6 | 21 | Done
Heat Map | Generate player heat maps for each clip analysed | 1 | 4 | 24 | Done
Setup Database | Setup a database to store all information for the site | 1 | 8 |  | Done
distinct tracking | manage player cross overs when tracking | 1 | 20 |  | Done
Acount Recovery | Recovery option for users | 10 | 4 | 8 | To Do
Distance Travelled | Display movement areas and distance covered by a player | 2 | 10 | 3 | Done | DT = Dev Team
Register Account | Create an option for user registration on the site | 2 | 10 | 4 | Done | SM = Scrum Master
Login/Logout | Create login and logout option for users | 2 | 8 | 7 | Done
Player Stats | Allow a user to see player stats | 2 | 6 | 11 | Done
Upload Clips | abilitiy for users to upload clips to be analysed | 2 | 6 | 14 | Done
user friendly interface | make sure website is easy to navigate | 2 | 4 |  | Done
Website Design | Design the layout for the website | 2 | 8 |  | Done
Create Annotations | Allow coaches to create annotations on videos (time Stamps) | 3 | 6 | 6 | To Do
Account details | allow a user to add more niformation to their account (number, email) | 4 | 2 | 17 | To Do
search Clips | allow a user to search for certain clips | 2 | 2 | 18 | Done
Favourite Clips | Allow users to save their favourite clips | 8 | 2 | 10 | To Do
Css | make the website look good | 2 | 16 |  | Done
Polish | finish up any tasks that need doing | 1 | 20 |  | Done
Run external Clips | Setup django to run custom scripts e.g Tracking Scripte | 1 | 20 |  | Done

## Options
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Myles
To Do | Doing | Jake
Done | Done | Will
| OK | Jacob
Myles / Jake
Will / Jacob
EveryOne
SM = Scrum Master
PO = Product Owner (teaching team)
DT = Development Team